Southern Metropolitan Region

Financial Stress in Growth Areas FIGA

State Government

Local Government

Community Organisations

Financial Sector

Community

Roadmap of action 2011 – 2014

Background

Southern Metropolitan Region (SMR) has experienced rapid, large growth in both population and number of households. The two main growth areas are in Cranbourne (within the City of Casey) and Pakenham/Officer district (within the Cardinia Shire).  Data and service provision indicators from across the partnership indicate that many families who move into these growth areas are suffering financial stress, often for the first time.  Mortgages, other credit lines and increased costs of travel are some of the triggers for families not being able to cope financially.

In 2010, partners from state and local government, community service organisations and other financial sector organisations met to discuss and address the issue of financial stress in the growth corridor in City of Casey and Cardinia Shire.  The session examined the issue of increasing financial stress in a sector under heavy demand in an area experiencing extended growth. The participants identified and explored initiatives to improve the service system response to financial stress through enhancing our existing systems and evolving the capacity of the system.  This is that plan.

Key Priority Area One: Establish a sustainable and effective cross agency governance arrangement

Key Priority Area Two: Develop an understanding of the existing service sector

Key Priority Area Three: Enhance capacity of existing and future workforce

Key Priority Area Four: Increase community awareness, with a focus on prevention and early intervention

(Timelines: Short 6-12 months; Medium 12mths, Long 24+ mths)

|  | Key Priority Area One: Establish a sustainable and effective cross agency governance arrangement |  |  |  |
| --- | --- | --- | --- | --- |
|  | Objective 1.1 Develop a multi-disciplined leadership group |  |  |  |
|  | Action | Outcome/Deliverable | Time frame | Lead Agency | Status |
| 1.1.1 | Establish a governance structure to efficiently facilitate agreed outcomes | Agreed governance structure is established | Short | W Group | A governance structure to efficiently facilitate agreed outcomes has been established and running effectively for 18 months |
| 1.1.2 | Generate a shared vision and values | A vision statement and a common set of values is created | Short | DoJ | A shared vision and values statement has been developed |
| 1.1.3 | Develop a set of shared outcomes | A list of identified shared outcomes is established | Short | W Group | A shared set of outcomes has been developed |
| 1.1.4 | Develop an accountability structure and performance monitoring process | Accountability regarding progress towards identified outcomes is easily and regularly monitored and reported | Short | W Group | Minutes and reporting have been managed by DHS as secretariat for the last 18 months FIGA is a standing agenda item for report back at the Regional Joint executive Forums held periodically across the region |
| 1.1.5 | Develop a plan to create shared resources | Resources to support the integrated work of the partner agencies are identified and committed to, including external funding options explored | Long | W Group |  |

|  | Objective 1.2 Identify engagement and reporting pathways that will maximise opportunities for success |
| --- | --- |
|  | Action | Outcome/Deliverable | Time frame | Lead Agency | Status |
| 1.2.1 | Identify and engage key stakeholder organisations, groups and individuals | Stakeholder organisations, groups and individuals are identified and engaged to support the initiative | Short | DHS | New members for the FIGA that have joined the group in 2011include: Manager of the Dandenong Money Hub Community Engagement Officer MECU Bank Financial Information Officer Cranbourne Centrelink RMIT Researcher for Selandra Rise CEO Financial and Consumer Rights Council Community Engagement Worker Stocklands Place Manager City of Casey Selandra Rise Project Community Engagement Officer ASIC Consumer Affairs Victoria |
| 1.2.2 | Link with relevant government committees to advocate for identified systems change | Interdepartmental Committee on Financial Hardship and SMR Regional Management Forum are engaged and regular reporting mechanisms established | Medium | DGS DoJ | On going - what is the status of the IDC? |
| 1.2.3 | Establish and maintain communication strategy | Ongoing formal and informal communication flow established to agency partners and community | On going | DHS | A FIGA social media hub has been set up on the VPS hub to facilitate the sharing of ideas and information as well as meeting agendas and minutes. |

|  | Key Priority Area Two: Develop an understanding of the existing service sector |  |  |  |
| --- | --- | --- | --- | --- |
|  | Objective 2.1: Develop a service mapping system |  |  |  |
|  | Action | Outcome/Deliverable | Time frame | Lead Agency | Status |
| 2.1.1 | Create an updatable resource map | Existing resources services are identified and categorised | Medium | DoJ |  |
|  |  | Service gaps are identified and mapped against priority locations |  |  |  |
|  |  | A plan to address the needs of high priority target groups is established |  |  |  |

|  | Objective 2.2: Develop an understanding of critical indicators of financial stress |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Outcome/Deliverable | Time frame | Lead Agency | Status |
| 2.2.1 | Develop key early indicators of financial stress | Through research of the literature and engagement with key organisations (banking and broader financial lending sector, utilities, Centrelink, local Government and other organisations) establish a measurable set of indicators | Medium | DHS |  |
| 2.2.2 | Establish a partnership approach to early intervention for individuals and families | Using these indicators, establish process for identifying individuals and families at risk and strategies for preventative intervention | Medium | DHS |  |

|  | Key Priority Area Three: Enhance capacity of existing and future workforce |
| --- | --- |
|  | Objective 3.1: Identify capacity of existing workforce to respond to financial stress |
|  | Action | Outcome/Deliverable | Time frame | Lead Agency | Status |
| 3.1.1 | Undertake research to identify existing workforce capacity to identify and respond to clients at risk of, or entering into financial stress | Gaps in capacity are identified. | Medium | DHS | DHS has completed research to form a summary of information around evidence base for information and a review of financial hardship of contemporary migrants and refugees. |
| 3.1.2 | Implement capacity building activities where need is identified | A region-wide, planned approach to building workforce capacity is established and implemented | Medium |  |  |
|  |  | Resources for implementation are identified | Medium |  |  |
|  |  | Strengthened knowledge across the sector is achieved | Long |  |  |

|  | Objective 3.2: Establish process for sustainable sector engagement and action |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Outcome/Deliverable | Time frame | Lead Agency | Status |
| 3.2.1 | Create sustainable regional response groups | Interest groups are established and actively share knowledge and initiate contemporary, collaborative responses and solutions | Medium |  |  |
|  | Identify opportunities to build on existing initiatives | Current initiatives are engaged and opportunities for linkage identified and implemented | Medium | DHS | There have been presentations to the group by: National Australia Bank and Good Shepherd Youth and Family Service Energy and Water Ombudsman Victoria VEDA Advantage Australian Securities Investment Commission Consumer Action Law Centre Stocklands |

|  | Key Priority Area Four: Increase community awareness, with a focus on prevention |
| --- | --- |
|  | Objective 4.1: Establish social change and acceptance of the need to ask for help at the earliest stages |
|  | Action | Outcome/Deliverable | Time frame | Lead Agency | Status |
| 4.1.1 | Identify community information needs, with a primary focus on prevention | Key community engagement messages are identified | Medium |  |  |
| 4.1.2 | Develop a shared community engagement model | A community engagement strategy is developed and implementation resources identified | Medium |  |  |
|  |  | Community engagement strategy is implemented and evaluated | Long |  |  |